## Sheet1
Test Closure Report
Manual Test Cases
Tests Executed
Number of Tests Executed | Number of Passed Test Cases | Passed Percentage | Number of Failed Test Cases
10 | 7 | 70% | 3
Defect Analysis
Defect Metrics
Priority | No. Defects Opened | No. Defects Closed | No. Defects On Hold | No. Defects Rejected
Critical
High | 3 | 0 | 0 | 0
Medium
Low
Outstanding Issues
0
Change Requests
0
Exit Criteria Status
TCs No. | Exit Criteria | Criteria Met? (Yes/No) | If No, Describe Plan of Action
1 | Dashboards dropdown is visible and the dropdown should show the available user specific dashboards | Yes
2 | This should give the pop up that assist you with steps to create a new dashboard . | Yes
3 | Create New Dashboard option should be there under Dashboards | No | Defect needs to be fixed by developer.
4 | There should be a pop-up to set it as HomePage. | Yes
5 | Should be able to click the button and work on that further. | No | Defect needs to be fixed by developer.
6 | All icons should be visible on the left side of the Dasshboard. | Yes
7 | Intercom button should give you the assisting chat box to help you with any query. | Yes
8 | Without name given Duplicate dashboard should not be created. | Yes
9 | The dashboard name should be editable with the editable icon shown for it. | No | Defect needs to be fixed by developer.
10 | No display of result for irrelevant keyword search | Yes